## Sheet2
Component | Tasks to be done | Assigned to | Status | ETA | Notes
Get emails from outlook | Create a project folder path. Create a folder to store all the downloaded email attachements Create a folder to track the logs (OCR data, status of the invoice) Download all the attachements of unread emails and store it in the folder | Akshat |  | 2025-07-08
Extract OCR data | Check if the attachment is a pdf and extract the ocr data of the invoice send the ocr data to the log files to keep track. If any required data in the extracted OCR is missing or need to be validated send it to exception for user to manually check and fix it Extract the vendor ID through API (crs620) | Jayaram/Kushal |  | 2025-07-15
classify whether PO or NONPO | Check if PO number is present in the extracted OCR If yes, then route the flow to PO flow, else to NONPO flow. | Jayaram/Kushal |  | 2025-07-16
PO flow | Check if the purchase order is exists in M3 (PPS200) If yes, then register the invoice in APS450, else send it to exception as Purchase order not available. Extract all the required data if any (Division) through APIs or business rules to create the header in APS450. | Sekhar/Akshat |  | 2025-07-25
NONPO flow | Extract the supplier number based on the supplier name(required to register a NONPO) If Supplier number is not found, send it to exception. Else register it in APS450. | Kushal/Jayaram |  | 2025-08-01
send to IDM | create two document types to store failure and success invoices. If for any reason, invoice got failed/ went in to exception then send it to failure document type. If the invoice successfully got registered then send it to success document type. | Sekhar |  | 2025-08-08